## Local Profiles Tracker
Section | Task | Platform | Status | Priority | Completed Date | Details | Notes
Prep | Confirm official business name | All | Done | High |  | Alex & Arms Ceramica
Prep | Confirm canonical address format | All | Not Started | High
Prep | Confirm primary phone number | All | Not Started | High
Prep | Confirm primary website URL | All | Not Started | High
Prep | Prepare business description (short) | All | Not Started | High
Prep | Prepare business description (long) | All | Not Started | Medium
Prep | Collect logo + cover + showroom photos | All | Not Started | High
Google Business Profile | Claim or request access | Google | Done | High | 2026-02-21
Google Business Profile | Set primary and secondary categories | Google | Not Started | High
Google Business Profile | Add exact NAP details | Google | Not Started | High
Google Business Profile | Add website link | Google | Not Started | High |  | alexandarms.com
Google Business Profile | Upload quality photos | Google | Not Started | Medium
Google Business Profile | Set business hours + special hours | Google | Not Started | High
Google Business Profile | Enable messaging/call options (if managed) | Google | Not Started | Medium
Google Business Profile | Start review collection + response flow | Google | Not Started | High
Bing Places | Create or claim listing | Bing | Done | High | 2026-02-21
Bing Places | Import from Google and verify details | Bing | Done | Medium | 2026-02-21 | 2026-02-21
Bing Places | Ensure NAP/category consistency | Bing | Not Started | High
Bing Places | Complete verification | Bing | Not Started | High
Apple Business Connect | Create or claim listing | Apple | Not Started | High
Apple Business Connect | Verify NAP consistency | Apple | Not Started | High
Apple Business Connect | Confirm map pin accuracy | Apple | Not Started | High
Apple Business Connect | Add photos, hours, website | Apple | Not Started | Medium
Consistency | Check name consistency across all profiles | All | Not Started | High
Consistency | Check address consistency across all profiles | All | Not Started | High
Consistency | Check phone consistency across all profiles | All | Not Started | High
Consistency | Check hours consistency across all profiles | All | Not Started | Medium
Citations | Create citation tracking sheet | All | Not Started | Medium
Citations | Submit to trusted local directories | All | Not Started | Medium
Citations | Track listing URL, status, updated date | All | Not Started | Medium
Monthly Maintenance | Add fresh photos monthly | All | Not Started | Low
Monthly Maintenance | Check duplicate listings | All | Not Started | Medium
Monthly Maintenance | Respond to all new reviews | All | Not Started | High
Monthly Maintenance | Review profile insights | All | Not Started | Medium

## Legend & How To Use
How to use this tracker
1) Update Status, Priority, Completed Date, and Notes for each task.
2) Use Status dropdown in column D and Priority dropdown in column E.
3) Keep NAP (Name, Address, Phone) consistent across all profiles.
4) Use Notes for links or evidence if needed.
Status colors:
Not Started
In Progress
Blocked
Done